## Ark 1
Frukt og Saft Website |  |  | WEEK 6 | [6 empty] | WEEK 7 | [6 empty] | WEEK 8 | [6 empty] | WEEK 9 | [6 empty] | WEEK 10
Start Date: monday 03.02.2020 ¦ Project duration: 5 weeks |  |  | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU
Initial Stage - 6 days | bar: WEEK 6 M to WEEK 6 F; WEEK 7 M to WEEK 7 F; WEEK 8 M to WEEK 8 F; WEEK 9 M to WEEK 9 F; WEEK 10 M to WEEK 10 F
Client meeting 9:30 | Whole Team | 1 hr | bar: WEEK 6 M
Web site UX Design - 1st stage | E. Thorsplass | 1 d | bar: WEEK 6 M
Logo and color scheme | T. Melhus | 2 d | bar: WEEK 6 T to WEEK 6 W
Web site UX design - revision | T. Melhus | 1 d | bar: WEEK 6 TH
Web site UX design - finalizing | E. Thorsplass | 2 d | bar: WEEK 6 F; WEEK 7 M
Team meeting 9:30 | Whole Team | 0.5 hr | bar: WEEK 7 M
Product Catalog - 11 days | bar: WEEK 6 M to WEEK 6 F; WEEK 7 M to WEEK 7 F; WEEK 8 M to WEEK 8 F; WEEK 9 M to WEEK 9 F; WEEK 10 M to WEEK 10 F
Product Photography | H. Knudsen | 4 d | bar: WEEK 7 M to WEEK 7 TH
Product & spec. copy | H. Hyttedal | 3 d | bar: WEEK 7 T to WEEK 7 TH
Product page UX & Front-end | E. Thorsplass | 5 d | bar: WEEK 7 T to WEEK 7 F; WEEK 8 M
Server-side dev. & implementation | V. Artemovich | 7 d | bar: WEEK 7 TH to WEEK 7 F; WEEK 8 M to WEEK 8 F
Progress meeting w/ client 15:30 | ET, VA, TM | 1 hr | bar: WEEK 9 M
Home Page and Promotions - 11 days | bar: WEEK 6 M to WEEK 6 F; WEEK 7 M to WEEK 7 F; WEEK 8 M to WEEK 8 F; WEEK 9 M to WEEK 9 F; WEEK 10 M to WEEK 10 F
Promotion banners & graphics | T. Melhus | 4 d | bar: WEEK 7 M to WEEK 7 TH
Blog & promotion copy | H. Hyttedal | 3 d | bar: WEEK 7 F; WEEK 8 M to WEEK 8 T
Banner & promotion photography | H. Knudsen | 3 d | bar: WEEK 8 M to WEEK 8 W
Home page & blog UX & front-end | E. Thorsplass | 5 d | bar: WEEK 8 T to WEEK 8 F; WEEK 9 M
Team meeting 17:00 | Whole Team | 1 hr | bar: WEEK 9 M
Membership & Shopping - 8 days | bar: WEEK 6 M to WEEK 6 F; WEEK 7 M to WEEK 7 F; WEEK 8 M to WEEK 8 F; WEEK 9 M to WEEK 9 F; WEEK 10 M to WEEK 10 F
Server-side dev. & implementation | V. Artemovich | 7 d | bar: WEEK 9 M to WEEK 9 F; WEEK 10 M to WEEK 10 T
Member/shopping front-end | E. Thorsplass | 7 d | bar: WEEK 9 T to WEEK 9 F; WEEK 10 M to WEEK 10 W
Developer meeting 8:30 | ET & VA | 2 hr | bar: WEEK 9 T
Remaining illustration & graphics | T. Melhus | 3 d | bar: WEEK 9 F; WEEK 10 M to WEEK 10 T
Project finalization - 2 days | bar: WEEK 6 M to WEEK 6 F; WEEK 7 M to WEEK 7 F; WEEK 8 M to WEEK 8 F; WEEK 9 M to WEEK 9 F; WEEK 10 M to WEEK 10 F
UX & functionality meeting 8:30 | ET, VA, TM | 1.5 hr | bar: WEEK 10 TH
Dev. wrap-up & finalization | ET & VA | 2 d | bar: WEEK 10 TH to WEEK 10 F
Client presentation 18:30 | Whole Team | 1 hr | bar: WEEK 10 F
Team Members
Front-end Developer: | Emil Thorsplass |  | WEEK 6 SU: in progress
Back-end Developer: | Vladimir Artemovich |  | WEEK 6 SU: meeting
Graphic Designer: | Tonje Melhus |  | WEEK 6 SU: final meeting
Copywriter: | Hanne Hyttedal
Photographer: | Hans Knudsen